## Overview
Stage 0 — Source Plan
Amazon India ¦ Prepared 2026-08-09 ¦ Working document for reviewer approval
Field | Working decision |  | Selection criterion | Why it matters | Status
Product | Amazon India |  | Market relevance | Large, visible consumer ecommerce apps in India | Proposed
Market | India |  | Journey coverage | Amazon covers search, evaluation, checkout, delivery, returns, and support | Proposed
Primary platform | Android / Google Play |  | Feedback abundance | Amazon has public app-store feedback and community discussion | Proposed
Secondary sources | iOS App Store, Reddit/community forums, industry reports |  | Depth potential | Single-product scope supports deeper segmentation and journey analysis | Proposed
Proposed period | 2025-08-09 through 2026-08-09
Target written reviews | 250 Amazon India reviews on Google Play; 50 on the India App Store where accessible
Approval gate | Do not begin Stage 1 collection until product scope, sample, and guardrails are approved
Method note: counts and ratings must be captured with access date and locale. Sample prevalence is directional and must not be reported as market prevalence.
Stage 0 approval checklist | Owner | Status | Reviewer decision | Date | Notes
Product scope approved | Reviewer | Awaiting approval
Market and time window approved | Reviewer | Awaiting approval
Source mix and sample approved | Reviewer | Awaiting approval
Privacy and access guardrails approved | Reviewer | Awaiting approval
Proceed to Stage 1 | Reviewer | Blocked pending approval

## Source inventory
Source Inventory
Primary sources identified during setup; Stage 1 will add capture dates, counts, and sampled records.
Source ID | Product | Source type | Source / publisher | URL | What it can support | Access constraint | Stage 0 status
S01 | Amazon India | Google Play listing | Google Play | https://play.google.com/store/apps/details?hl=en-US&id=in.amazon.mShop.android.shopping | App metadata, ratings, written reviews, data-safety disclosures | Counts/reviews can vary by locale and UI state | Seeded
S02 | Amazon India | Google Play listing | Google Play | https://play.google.com/store/apps/details?id=com.amazon.mShop.android.shopping | Global Amazon Shopping listing for cross-checking app identity | Not necessarily India-specific | Seeded
S03 | Amazon India | App Store reviews | Apple App Store | https://apps.apple.com/in/app/amazon-india-shop-pay-minitv/id1478350915 | iOS reviews and platform comparison | Country/storefront and pagination limitations | Seeded
S04 | Amazon India | Industry report | Euromonitor | https://www.euromonitor.com/retail-e-commerce-in-india/report | Market relevance and category context | Commercial report; public excerpt only | Context
S05 | Amazon India | Community discussion | Reddit / IndiaTech | https://www.reddit.com/r/IndiaTech/comments/1uujci6/amazon_has_the_worst_ux_out_of_any_shopping_app/ | Qualitative UX, returns, and preference signals | Self-selected and anecdotal | Seeded
S06 | Amazon India | Community discussion | Reddit / India | https://www.reddit.com/r/india/comments/1s36pbv/the_era_of_customerfirst_ecommerce_in_india_is_over/ | Longer-term trust and service narratives | Older discussion; use as context only | Candidate

## Query matrix
Query Matrix
Use these queries as a reproducible starting point; log exact query, date, locale, and result count during collection.
Query ID | Product | Source | Query / filter | Purpose
Q01 | Amazon India | Google Play | in.amazon.mShop.android.shopping sort:recent | Recent app feedback baseline
Q02 | Amazon India | Google Play | Amazon India app returns refund delivery payment crash | Theme-directed retrieval
Q03 | Amazon India | Google Play | Amazon India app seller fake review authenticity | Trust and seller quality
Q04 | Amazon India | App Store | Amazon India app reviews India | iOS platform comparison
Q05 | Amazon India | Reddit | Amazon India UX search returns delivery support | Qualitative journey narratives
Q06 | Amazon India | Reddit | Amazon India review authenticity seller trust | Trust and review narratives
Q07 | Amazon India | Web search | Amazon India ecommerce market position 2025 | Market context only
Q08 | Amazon India | Web search | Amazon India accessibility app reviews | Accessibility signals

## Sampling plan
Sampling Plan
Proposed sample is directional discovery evidence, not a statistically representative customer survey.
Product | Source | Target records | Stratification | Primary use | Minimum fields | Status
Amazon India | Google Play | 250 | Star rating: 1–2, 3, 4–5; recent-first within each band | Core discovery dataset | URL, date, rating, text, product, journey, theme | Proposed
Amazon India | App Store | 50 | Recent written reviews where accessible | Platform comparison | URL, date, rating, text, platform | Proposed
Amazon India | Reddit/community | 50 | Relevant public posts/comments; deduplicate threads | Deep qualitative context | URL, date, text/paraphrase, theme, context | Proposed
Amazon India | Industry/context | 10 | Only authoritative and relevant documents | Market and policy context | URL, date, publisher, claim, limitation | Proposed
Amazon India | Accessibility | 20 | Search for screen reader, contrast, font, keyboard, voice | Accessibility gap scan | URL, date, platform, evidence | Proposed
Total target | All sources | 380 | Adjust after access audit; report actual counts | Stage 1 evidence base | Full provenance and redaction | Pending approval

## Approval log
Approval Log
Reviewer-controlled gate: Stage 1 collection remains blocked until the decisions below are recorded.
Decision ID | Decision | Recommendation | Reviewer decision | Date | Notes / change request
A01 | Product scope | Approve Amazon India as the sole product in scope | Awaiting approval
A02 | Market and window | Approve India and 2025-08-09 to 2026-08-09 | Awaiting approval
A03 | Source mix | Approve Android-first plus iOS/community/context sources | Awaiting approval
A04 | Sample plan | Approve target of up to 380 records, adjusted for access | Awaiting approval
A05 | Guardrails | Approve privacy, provenance, and access restrictions | Awaiting approval
A06 | Stage 1 gate | Proceed to discovery collection only after A01–A05 are approved | Blocked

## Frameworks & tools
Frameworks & Tool Usage
Portfolio showcase: the method and tool used for each product-management decision.
Product stage | Framework / method | Usage | Artifact | Tool examples
Research setup | Research canvas + hypothesis tree | Define what must be learned before collection | Research brief and hypothesis register | Notion / Confluence
Discovery | Thematic analysis + JTBD | Turn reviews into recurring needs and desired outcomes | Coded dataset and theme report | Excel / Google Sheets
Customer understanding | Personas + journey mapping | Show who experiences the problem and where | Persona and current-state journey | FigJam / Miro
Problem definition | 5 Whys + opportunity solution tree | Separate symptoms from root problems | Problem statement and opportunity tree | FigJam / Miro
Prioritization | RICE + confidence scoring | Rank opportunities using reach, impact, effort, and evidence | Opportunity scoring workbook | Excel / Google Sheets
Solution discovery | Design Sprint + Kano | Generate and narrow solution concepts | Concept comparison and prototype | Figma / FigJam
Product definition | PRD + story mapping + INVEST | Translate the solution into an actionable MVP | PRD, stories, acceptance criteria | Notion / Confluence / Jira
Delivery planning | Dual-track Agile + RACI | Coordinate discovery, delivery, ownership, and dependencies | Release plan and RAID log | Jira / Linear
Validation | Usability testing + experiment design | Test desirability, usability, feasibility, and viability | Test plan and iteration backlog | Figma / Sheets
Launch | Go/no-go + phased rollout | Control launch risk and define rollback conditions | Launch checklist and go/no-go memo | Jira / Slack
Measurement | North Star + AARRR/HEART + cohorts | Measure customer and business outcomes | Tracking plan and outcome review | Amplitude / Mixpanel / GA4